## D&D Overview
Techjays Design & Discovery (D&D) Document Guide
Reference guide to the documents that make up a D&D pack. The pack is the Scope & Agreement + Solution & Plan artifact set produced in lifecycle phases 2-4 (Scoping, Solutioning, Planning & Prepare) of the Excellence Command Center, and is the evidence base the PSRC reviews before execution starts. Each document answers one question, has one owner, and earns one sign-off. See the Lifecycle & Governance tab for how the pack fits the Command Center.
# | Document | Question it answers | Owner | Approves (sign-off)
1 | Executive Summary / Engagement Brief | Why are we doing this, what outcome, what's recommended? | Engagement lead | Orientation & recommended approach
2 | Scope Document (incl. Requirements) | What are we building? What's in / out? What are the rules? | BA / Engagement lead | The scope-freeze baseline
3 | Technical Architecture & Solution Design | How will it work technically? AI vs deterministic, data, integrations, NFRs? | Architect / Tech lead | Technical feasibility
4 | RAID Register (Risks, Assumptions, Issues, Dependencies) | Under what conditions does this estimate hold? | Engagement lead | The conditions attached to the price
5 | Implementation Plan & Phasing | In what order and over what timeline (Learn / Proof / Ship / Evolve)? | Delivery lead | Sequencing & phasing
6 | Approval / Sign-off Page | Is this baseline agreed by the client? | Client signatories | The scope freeze itself

## 1. Executive Summary
Executive Summary / Engagement Brief
Owner: Engagement lead. The orientation document often the only one a sponsor reads end-to-end. Keep it short and decision-oriented.
# | Key section | What it should cover | Owner
1 | Engagement context & business driver | Why this engagement exists; the business problem or opportunity in the client's terms; trigger for acting now. | Engagement lead
2 | Current-state summary | One-paragraph synthesis of how things work today and the cost of the status quo (time, error, risk). Detail lives in the Scope Document. | Engagement lead
3 | Future-state vision | The target AI-native outcome in plain language; what changes for the business and its users. | Engagement lead
4 | Recommended approach | Techjays' proposed path, including the outcome-based / shared-risk model and the Learn-Proof-Ship-Evolve framing. | Engagement lead
5 | Scope at a glance | The modules in play and any headline exclusions, summarised. Points to the Scope Document for detail. | Engagement lead
6 | Commercial model note | How the engagement is priced at a high level (fixed-bid where ready, T&M where not). No numbers if the proposal is separate. | Engagement + Commercial
7 | Key risks & assumptions (headline) | The 3-5 things that most affect feasibility, cost, or timeline. Full list lives in the RAID Register. | Engagement lead
8 | Decision requested | Exactly what the client is being asked to approve at this milestone, and what unlocks next. | Engagement lead

## 2. Scope Document
Scope Document (including Requirements)
Owner: BA / Engagement lead. The heart of the pack and the thing that gets frozen. Requirements here are at module / capability level — the detailed SRS comes later in build.
# | Key section | What it should cover | Owner
1 | Scope statement | A clear sentence defining the boundary of what is being delivered; sets the frame for everything below. | BA / Engagement lead
2 | Module breakdown | The business decomposed into modules (e.g. Intake, Processing, Validation, Approval, System Updates, Exception Handling, Reporting, Admin, Integrations). Each gets its own sign-off. | BA / Engagement lead
3 | Per-module: Current state | How the process works today — actors, triggers, inputs/outputs, systems, manual steps, pain points, known exceptions. | BA
4 | Per-module: Future state | How the AI-enabled process will work — AI role, software automation role, human approval points, exception flow, system updates, audit trail. | BA
5 | Per-module: In scope / Out of scope | Functional capabilities, document/data types, workflows and integrations included; and explicitly what is excluded, deferred, or unconfirmed. | BA / Engagement lead
6 | Per-module: Functional requirements | Capability-level requirements (what the module must do), each prioritised. Detailed, testable specs are deferred to the SRS. | BA
7 | Per-module: Business rules | Approval rules, matching rules, validation rules, escalation rules. | BA
8 | Per-module: Exceptions | Missing data, duplicates, API failures, low AI confidence, mismatches, delayed approvals — and how each is handled. | BA
9 | Per-module: Data fields | Key inputs/outputs and the fields the module reads or writes. | BA / Architect
10 | Per-module: Integrations | Systems the module touches and the direction of data flow. | BA / Architect
11 | Per-module: Acceptance criteria | What must be true for the module to be considered complete and acceptable. | BA / Engagement lead
12 | AI vs deterministic responsibility split | Explicit dividing line: what AI may decide (probabilistic), what stays deterministic (rule-based), where a human must confirm. Governs every module. | Architect / BA
13 | User roles & permissions | The user classes and what each can do. | BA
14 | Global out-of-scope | Cross-cutting exclusions that apply beyond a single module. | Engagement lead
15 | Assumptions reference | Pointer to the RAID Register; assumptions are owned there, not duplicated here. | Engagement lead

## 3. Technical Architecture
Technical Architecture & Solution Design
Owner: Architect / Tech lead. Answers HOW the solution works. Confirms technical feasibility behind the scope.
# | Key section | What it should cover | Owner
1 | Solution overview & context diagram | High-level architecture and how the system sits among the client's existing systems; end-to-end flow across modules. | Architect
2 | Component architecture | The major components/services and how they interact; sequence of a representative end-to-end transaction. | Architect
3 | AI / ML approach | Capability types (extraction, classification, summarisation, generation, retrieval), model/service choices, hosting, and the data-flow boundary. | Architect / ML lead
4 | Deterministic logic boundary | What is implemented as deterministic, testable software vs handed to AI; confidence thresholds and human-in-the-loop points. | Architect
5 | Data architecture & dictionary | Core entities, data stores, the master field list/schema, and how data moves through the system. | Architect / Data
6 | Integration specifications | Each external system: direction (read/write), protocol/API, authentication, rate limits and known constraints. (Break into its own doc only if integration is the dominant risk.) | Architect
7 | Non-functional requirements (NFRs) | Measurable targets for performance, scalability, availability, reliability, usability/accessibility — not adjectives. | Architect
8 | Security & compliance | AuthN/AuthZ, encryption in transit/at rest, SSO, PII handling, data residency, retention, audit trail, regulatory obligations. | Architect / Security
9 | Environments & deployment | Deployment model (cloud/region/on-prem/hybrid), environments, and release approach. | Architect / DevOps
10 | Technical constraints | Mandated technologies, platform limits, volume ceilings, or client-imposed constraints that shape the design. | Architect
11 | Responsible AI & guardrails | Restricted actions, redaction, content-safety / prompt-injection controls, and the rule that AI never finalises irreversible actions without the defined human step. | Architect / ML lead
12 | Monitoring & drift (Evolve) | Production accuracy monitoring, alerting on degradation, retraining triggers. | Architect / ML lead

## 4. RAID Register
RAID Register - Risks, Assumptions, Issues, Dependencies
Owner: Engagement lead. The living document most teams skip and most regret. These are the conditions under which the fixed price is valid.
# | Key section | What it should cover | Owner
1 | Assumptions | Each assumption the estimate relies on, with impact-if-wrong. E.g. accuracy expectations, sample-data availability, third-party limitations. Failing assumptions trigger change control. | Engagement lead
2 | Dependencies | What Techjays needs from the client or third parties and by when: system/credential access, API availability, sample data, stakeholder availability for clarifications and UAT. | Engagement lead
3 | Risks | Things that may go wrong, with likelihood, impact, mitigation, and owner. Includes technical, data, integration, and delivery risks. | Engagement lead
4 | Open questions | Unresolved items, each classified using the D&D scheme (see classification row). Drives whether a module can be estimated. | Engagement lead
5 | Open-question classification | Apply one per question: Must close before estimate · Proceed with assumption · Minor implementation detail · Too uncertain (exclude / T&M) · Future phase. | Engagement lead
6 | Resolution log / status | Tracks each item to closure: status, owner, date needed, date resolved. Keeps the register live rather than a one-time snapshot. | Engagement lead

## 5. Implementation Plan
Implementation Plan & Phasing
Owner: Delivery lead. Sequences the approved scope across the Learn / Proof / Ship / Evolve model.
# | Key section | What it should cover | Owner
1 | Phase breakdown | The engagement structured as Learn → Proof → Ship → Evolve, with the goal of each phase. | Delivery lead
2 | Module-to-phase mapping | Which modules land in which phase, and why (value, risk, dependency order). | Delivery lead
3 | Milestones & deliverables | Concrete deliverables and decision points per phase. | Delivery lead
4 | Sequencing & dependencies | Build order and inter-module/technical dependencies that constrain it. | Delivery lead / Architect
5 | Timeline view | Indicative schedule across phases; durations and key dates (caveated by RAID assumptions). | Delivery lead
6 | Resource & cost plan | Team shape, roles, and effort per phase, with the cost basis. Feeds the PSRC 'Effort & Timeline' review lens. | Delivery lead
7 | Communication plan | Cadence, channels, and stakeholders for status, escalation, and decisions across the engagement. | Delivery lead
8 | Quality & acceptance plan | How quality is assured and how acceptance is demonstrated per phase; ties to module acceptance criteria and UAT sign-off. | Delivery lead / QA
9 | Entry / exit criteria per phase | What must be true to start and to close each phase — ties phases to acceptance. | Delivery lead

## 6. Approval Page
Approval / Sign-off Page
Owner: Client signatories + internal PSRC. Two gates: the PSRC (internal) approves the solution & scope to proceed, and the client signs off the scope freeze that authorises Techjays to prepare the fixed-bid proposal.
# | Key section | What it should cover | Owner
1 | Scope-freeze statement | States that the documented modules, workflows, assumptions, integrations, business rules, exceptions, exclusions, and acceptance criteria are approved as the baseline for a fixed-bid proposal. | Engagement lead
2 | What is being approved | Explicit list of what the signature covers (the contents of the pack as a baseline). | Engagement lead
3 | Exclusions acknowledgement | Client acknowledges what is out of scope, deferred, or T&M-recommended, so nothing is assumed included by silence. | Engagement lead
4 | Internal PSRC review & approval | The Project Solution Review Committee reviews scope & solution for Solution Fit, Scope Completeness, Architecture Soundness, Risk & Feasibility, Effort & Timeline, Value & ROI, and Client Impact. PSRC approval is the internal gate that authorises proceeding (Approve to Proceed → Execution Starts). | PSRC / Head of Command Center
5 | Change-control note | Any new requirement, workflow, integration, report, rule, exception, data variation, third-party limitation, or changed assumption after approval may affect cost, timeline, and approach, and is handled via change control. | Engagement lead
6 | Signatory table | Names, roles, organisations, signatures, and dates for the client and Techjays approvers. Records both the internal PSRC approval and the client sign-off. | Client + Techjays